## Grantee Quarterly Report
Alternative Fuel Infrastructure Grant Program
Grantee Quarterly Operation Report
Grantee Name: |  |  |  | Electric Vehicle Institute
Dates Report Covers: |  |  |  | 2Q18 ¦ 1 APRIL 2018 - 30 JUNE 2018
Submitted By: |  |  |  | Matthew Wade
Email Address |  |  |  | wadem@ev-institute.com
Report Date: |  |  |  | 2018-07-15
Please provide a brief narrative on the project progress, including any challenges, that occurred during the reporting period:
The AFIP project has been successful from both an operation and deployment perspective. EVI has successfully completed the construction phase of AFIP FY2016 and deployed all fourteen stations as listed in this report. Moreover, EVI continues to perform its preventive maintenance and operation plan of all fourteen stations. In regards to unscheduled maintenance/repair, EVI performed onsite services, which have been outlined below: 1. EVI continues to work with BGE and the Recreation and Parks Department to repair broken utility meter/transformer to normalize service to Gwynn Fall Park station - this is expected to be completed by AUGUST 2018; 2. Replaced faulty CCS Combo connector and repaired safety relay power source at City Garage; 3. Replaced faulty CCS Combo connector and repaired safety relay power source at Patterson Park; 4. Replaced faulty CCS Combo connector and repaired safety relay power source at Roland Park Library Branch; 5. EVI is working with BGE and Facility Engineers to repair electrical room at Forest Park Library Branch; and 6. Replaced faulty external transformer at Reisterstown Road Library Branch.
Station Location
Station Address | City | Zip | County | Effective Status Date | Fuel Type | % of Time Operational | kWh Consumed | # Of Gasoline Equivalent Gallons Displaced | Average Charging Event Duration (minutes) | # Of Charging Sessions | Average Alternative Fuel Price ($/kWh)
6310 Reisterstown Road | Baltimore | 21215 | Baltimore City | 2016-09-07 | 50kW - DC Fast Charger | 100% | 2529.95 | 75.0727 | 41.3333 | 143 | Free
1303 Orleans Street | Baltimore | 21231 | Baltimore City | 2016-08-16 | 50kW - DC Fast Charger | 100% | 3197.04 | 94.8677 | 35.5 | 188 | Free
1101 Russell Street | Baltimore | 21230 | Baltimore City | 2016-09-29 | 50kW - DC Fast Charger | 100% | 397.34 | 11.7905 | 24.3333 | 32 | Free
1251 Light Street | Baltimore | 21230 | Baltimore City | 2016-10-07 | 50kW - DC Fast Charger | 100% | 5944.8 | 176.4036 | 16.6667 | 652 | Free
5910 Harford Road | Baltimore | 21214 | Baltimore City | 2016-11-10 | 50kW - DC Fast Charger | 100% | 7323.78 | 217.3228 | 28 | 536 | Free
5108 Roland Avenue | Baltimore | 21210 | Baltimore City | 2016-11-18 | 50kW - DC Fast Charger | 100% | 5982.96 | 177.5359 | 24.6667 | 491 | Free
3100 Swann Drive | Baltimore | 21217 | Baltimore City | 2017-01-06 | 50kW - DC Fast Charger | 100% | 11429.77 | 339.1623 | 27.3333 | 801 | Free
3023 Garrison Boulevard | Baltimore | 21216 | Baltimore City | 2016-12-13 | 50kW - DC Fast Charger | 86% | 8383.47 | 248.7677 | 27.5 | 547 | Free
3801 Erdman Avenue | Baltimore | 21213 | Baltimore City | 2017-02-06 | 50kW - DC Fast Charger | 100% | 8023.86 | 238.0967 | 26.3333 | 604 | Free
3001 Boston Street | Baltimore | 21224 | Baltimore City | 2017-03-08 | 50kW - DC Fast Charger | 100% | 6031.38 | 178.9727 | 25 | 448 | Free
27 S Patterson Park Ave | Baltimore | 21231 | Baltimore City | 2017-03-17 | 50kW - DC Fast Charger | 100% | 1355.5 | 40.2226 | 21.6667 | 98 | Free
101 West Dickman Street | Baltimore | 21230 | Baltimore City | 2017-03-28 | 50kW - DC Fast Charger | 100% | 16262.14 | 482.5561 | 39.3333 | 752 | Free
4999 Windsor Mill Road | Baltimore | 21207 | Baltimore City | 2017-03-09 | 50kW - DC Fast Charger | 0% | 0 | 0 | 0 | 0 | Free
7000 Carroll Avenue | Takoma Park | 20912 | Montgomery | 2017-11-28 | 50kW - DC Fast Charger | 100% | 7443.06 | 220.8623 | 26.3333 | 506 | 0.64

## Sheet1
Pre-Permitting
In Permitting
Under Construction
Operational