## Grantee Quarterly Report
Alternative Fuel Infrastructure Grant Program
Grantee Quarterly Operation Report
Grantee Name: |  |  |  | Electric Vehicle Institute
Dates Report Covers: |  |  |  | 3Q18 ¦ 1 JULY 2018 - 30 SEPTEMBER 2018
Submitted By: |  |  |  | Matthew Wade
Email Address |  |  |  | wadem@ev-institute.com
Report Date: |  |  |  | 2018-10-15
Please provide a brief narrative on the project progress, including any challenges, that occurred during the reporting period:
The AFIP FY17 project has been successful from both an operation and deployment perspective. EVI has installed fourteen of twenty-two 50kW charging stations at four of the seven locations. EVI continues to perform its preventive maintenance and operation plan of all operating stations. Per past reports, the Clarion Inn Chargers were experiencing service and power interruptions from insufficient/deteriorating host facility and power conditions on site. Thus, MEA has approved the EVI's site change request to move the stations from the Clarion Inn to the nearby City of Frederick property. This move and operation are underway and in the final stages of the permitting process. In regards to unscheduled maintenance/repair, Station No. 11 located at the Chesapeake House Travel Plaza encountered a system failure that requires the replacement of the station's power inverter. As this repair is complex, a teir two technician has been contracted and is scheduled to complete this service by mid-October. Additionally, Station No. 1 located at the Takoma Park Community Center required the replacement of a communication component.
Station Location
Station ID | Location Name | Station Address | City | Zip | County | Effective Status Date | Fuel Type | % of Time Operational | kWh Consumed | # Of Gasoline Equivalent Gallons Displaced | Average Charging Event Duration (minutes) | # Of Charging Sessions | Average Alternative Fuel Price ($/kWh)
1 | Takoma Park Community Center | 7500 Maple Avenue | Takoma Park | 20912 | Montgomery | 2017-05-03 | 50kW - DC Fast Charger | 91% | 2856 | 84.7478 | 27 | 204 | 0.82
2 | Clarion Inn and Conference Center | 5400 Holiday Drive | Frederick | 21703 | Frederick | 2017-05-31 | 50kW - DC Fast Charger | 0% | 0 | 0 | 0 | 0 | -
3 | Clarion Inn and Conference Center | 5400 Holiday Drive | Frederick | 21703 | Frederick | 2017-05-31 | 50kW - DC Fast Charger | 0% | 0 | 0 | 0 | 0 | -
4 | Clarion Inn and Conference Center | 5400 Holiday Drive | Frederick | 21703 | Frederick | 2017-05-31 | 50kW - DC Fast Charger | 0% | 0 | 0 | 0 | 0 | -
5 | Clarion Inn and Conference Center | 5400 Holiday Drive | Frederick | 21703 | Frederick | 2017-05-31 | 50kW - DC Fast Charger | 0% | 0 | 0 | 0 | 0 | -
6 | Greenbelt Roosevelt Center | 25 Crescent Road | Greenbelt | 20770 | Prince Georges | 2017-08-09 | 50kW - DC Fast Charger | 100% | 14226 | 422.1365 | 26 | 1026 | Free
7 | Maryland House Travel Plaza | I-95, Mile Marker 82 | Aberdeen | 21001 | Hardford | 2017-10-11 | 50kW - DC Fast Charger | 100% | 905 | 26.8546 | 25 | 92 | Free
8 | Maryland House Travel Plaza | I-95, Mile Marker 82 | Aberdeen | 21001 | Hardford | 2017-10-11 | 50kW - DC Fast Charger | 100% | 736 | 21.8398 | 23 | 88 | Free
9 | Maryland House Travel Plaza | I-95, Mile Marker 82 | Aberdeen | 21001 | Hardford | 2017-10-11 | 50kW - DC Fast Charger | 100% | 1039 | 30.8309 | 29 | 74 | Free
10 | Maryland House Travel Plaza | I-95, Mile Marker 82 | Aberdeen | 21001 | Hardford | 2017-10-11 | 50kW - DC Fast Charger | 100% | 750 | 22.2552 | 33 | 52 | Free
11 | Chesapeake House Travel Plaza | I-95, Mile Marker 97 | North East | 21901 | Cecil | 2017-11-01 | 50kW - DC Fast Charger | 69% | 792 | 23.5015 | 22 | 71 | Free
12 | Chesapeake House Travel Plaza | I-95, Mile Marker 97 | North East | 21901 | Cecil | 2017-11-01 | 50kW - DC Fast Charger | 100% | 1561 | 46.3205 | 25 | 131 | Free
13 | Chesapeake House Travel Plaza | I-95, Mile Marker 97 | North East | 21901 | Cecil | 2017-11-01 | 50kW - DC Fast Charger | 100% | 1412 | 41.8991 | 23 | 119 | Free
14 | Chesapeake House Travel Plaza | I-95, Mile Marker 97 | North East | 21901 | Cecil | 2017-11-01 | 50kW - DC Fast Charger | 100% | 1619 | 48.0415 | 23 | 131 | Free