## Grantee Quarterly Report
Appendix A
Electric Vehicle Infrastructure Grant Program
Grantee Quarterly Operation Report
Grantee Name: |  |  |  |  | ChargePoint, Inc.
Dates Report Covers: |  |  |  |  | Q4'18 (October to December)
Report Submitted By: |  |  |  |  | John Schott
Email Address: |  |  |  |  | john.schott@chargepoint.com
Report Date: |  |  |  |  | 2019-01-25
Please provide a brief narrative on the project progress, including any challenges, that occurred during the reporting period:
ChargePoint is pleased to provide data related to the operation of MEA funded DC Fast Charging stations (DCFC) during Q4'18 - October to December. In total, the DC Fast Charging Stations installed by ChargePoint dispensed 545 kWh across 42 charging sessions or an average of 13 kWh per session. This level of utilization resulted in the displacement of 69 gallons of gasoline using the industry assumption of .1255 gallons saved per kWh. The average utilization time of the 50kW DCFC was 22 minutes per session, which can provide up to 200 miles of range per hour of charging (RPH) on the ChargePoint Express 200 stations. While three of the four stations were operational for 100% of the time this quarter, Hagerstown station #1 was down for the entire quarter. The station reported an error that resulted in a fuse and diode replacement, which was completed on January 17, 2019. The station is still reporting problems however and we have escalated the issue to Tritium, the station manufacturer, who is investigating a combo cable replacement among other issues. We will keep MEA updated on our progress towards bringing the station back online over the quarter. ChargePoint anticipates that these station's utilization will continue to increase as knowledge of their existence proliferates and EV adoption increases in the state of Maryland.
Station Location |  |  |  |  | Quarterly Data |  |  |  |  | Cumulative Data
Station Name | Station Address | City | Zip | County | % of Time Operational | kWhs consumed | Average Charging Event Duration (mins) | # Of Gasoline Gallons Displaced | # Of Vehicles Using EVSE | kWhs consumed | # Of Gasoline Gallons Displaced
DCEC / HAGERSTOWN #1 | 17513-17521 Valley Mall Rd | Hagerstown | 21740 | Washington County | 0% | 0 | 0 | 0 | 0 | 4026 | 505
DCEC / HAGERSTOWN #2 | 17513-17521 Valley Mall Rd | Hagerstown | 21740 | Washington County | 100% | 348 | 46 | 44 | 22 | 3936 | 494
ROYAL FARMS / RFS 102 DC #1 | 10740 Pulaski Hwy | White Marsh | 21162 | Baltimore County | 100% | 182 | 29 | 23 | 18 | 4047 | 508
ROYAL FARMS / RFS 102 DC #2 | 10740 Pulaski Hwy | White Marsh | 21162 | Baltimore County | 100% | 15 | 12 | 2 | 2 | 3682 | 462
|  |  |  | Total |  | 545 |  | 69 | 42 | 15691 | 1969
|  |  |  | Cumulative Avg. | 75% | 136.25 | 21.75 | 17.25 | 10.5