## Grantee Quarterly Report
Alternative Fuel Infrastructure Grant Program
Grantee Quarterly Operation Report
Grantee Name: |  |  |  | Electric Vehicle Institute
Dates Report Covers: |  |  |  | 4Q18 ¦ 1 OCTOBER 2018 - 31 DECEMBER 2018
Submitted By: |  |  |  | Matthew Wade
Email Address |  |  |  | wadem@ev-institute.com
Report Date: |  |  |  | 2019-01-15
Please provide a brief narrative on the project progress, including any challenges, that occurred during the reporting period:
The AFIP FY17 project has been successful from both an operation and deployment perspective. EVI has installed twenty of twenty-two 50kW charging stations at six of the eight locations. EVI continues to perform its preventive maintenance and operation plan of all operating stations. In regards to unscheduled maintenance/repair, EVI performed the following service(s): 1. Repaired the CCS Combo connector cable assembly at Staion No. 1; and 2. Calibrated system metering and addressed system communication issues at Station No. 7, 8 and 10.
Station Location
Station ID | Location Name | Station Address | City | Zip | County | Effective Status Date | Fuel Type | % of Time Operational | kWh Consumed | # Of Gasoline Equivalent Gallons Displaced | Average Charging Event Duration (minutes) | # Of Charging Sessions | Average Alternative Fuel Price ($/kWh)
1 | Takoma Park Community Center | 7500 Maple Avenue | Takoma Park | 20912 | Montgomery | 2017-05-03 | 50kW - DC Fast Charger | 97% | 1577 | 46.7953 | 31 | 119 | 0.82
2 | (CLARION INN) | - | Frederick | 21703 | Frederick | - | 50kW - DC Fast Charger | 0% | 0 | 0 | 0 | 0 | -
3 | (CLARION INN) | - | Frederick | 21703 | Frederick | - | 50kW - DC Fast Charger | 0% | 0 | 0 | 0 | 0 | -
4 | (CLARION INN) | - | Frederick | 21703 | Frederick | - | 50kW - DC Fast Charger | 0% | 0 | 0 | 0 | 0 | -
5 | (CLARION INN) | - | Frederick | 21703 | Frederick | - | 50kW - DC Fast Charger | 0% | 0 | 0 | 0 | 0 | -
6 | Greenbelt Roosevelt Center | 25 Crescent Road | Greenbelt | 20770 | Prince Georges | 2017-08-09 | 50kW - DC Fast Charger | 100% | 9841 | 292.0178 | 26 | 833 | Free
7 | Maryland House Travel Plaza | I-95, Mile Marker 82 | Aberdeen | 21001 | Hardford | 2017-10-11 | 50kW - DC Fast Charger | 100% | 435 | 12.908 | 10 | 116 | Free
8 | Maryland House Travel Plaza | I-95, Mile Marker 82 | Aberdeen | 21001 | Hardford | 2017-10-11 | 50kW - DC Fast Charger | 100% | 1568 | 46.5282 | 38 | 89 | Free
9 | Maryland House Travel Plaza | I-95, Mile Marker 82 | Aberdeen | 21001 | Hardford | 2017-10-11 | 50kW - DC Fast Charger | 100% | 263 | 7.8042 | 22 | 25 | Free
10 | Maryland House Travel Plaza | I-95, Mile Marker 82 | Aberdeen | 21001 | Hardford | 2017-10-11 | 50kW - DC Fast Charger | 100% | 862 | 25.5786 | 38 | 46 | Free
11 | Chesapeake House Travel Plaza | I-95, Mile Marker 97 | North East | 21901 | Cecil | 2017-11-01 | 50kW - DC Fast Charger | 100% | 1689 | 50.1187 | 24 | 137 | Free
12 | Chesapeake House Travel Plaza | I-95, Mile Marker 97 | North East | 21901 | Cecil | 2017-11-01 | 50kW - DC Fast Charger | 100% | 3053 | 90.5935 | 26 | 244 | Free
13 | Chesapeake House Travel Plaza | I-95, Mile Marker 97 | North East | 21901 | Cecil | 2017-11-01 | 50kW - DC Fast Charger | 100% | 1104 | 32.7596 | 25 | 103 | Free
14 | Chesapeake House Travel Plaza | I-95, Mile Marker 97 | North East | 21901 | Cecil | 2017-11-01 | 50kW - DC Fast Charger | 100% | 1954 | 57.9822 | 25 | 149 | Free
15 | Maryland House Travel Plaza | I-95, Mile Marker 82 | Aberdeen | 21001 | Hardford | 2018-10-12 | 50kW - DC Fast Charger | 100% | 821 | 24.362 | 36 | 54 | Free
16 | Maryland House Travel Plaza | I-95, Mile Marker 82 | Aberdeen | 21001 | Hardford | 2018-10-12 | 50kW - DC Fast Charger | 100% | 532 | 15.7864 | 32 | 45 | Free
17 | Hagerstown Central Parking Lot | 14 N Potomac Street | Hagerstown | 21740 | Washington | 2018-12-13 | 50kW - DC Fast Charger | 100% | 116 | 3.4421 | 29 | 10 | Free
18 | Hagerstown Central Parking Lot | 14 N Potomac Street | Hagerstown | 21740 | Washington | 2018-12-13 | 50kW - DC Fast Charger | 100% | 110 | 3.2641 | 34 | 8 | Free
19 | Hagerstown Central Parking Lot | 14 N Potomac Street | Hagerstown | 21740 | Washington | 2018-12-13 | 50kW - DC Fast Charger | 100% | 135 | 4.0059 | 30 | 9 | Free
20 | Hagerstown Central Parking Lot | 14 N Potomac Street | Hagerstown | 21740 | Washington | 2018-12-13 | 50kW - DC Fast Charger | 100% | 130 | 3.8576 | 22 | 12 | Free