## Grantee Quarterly Report
Appendix A
Alternative Fuel Infrastructure Grant Program
Grantee Quarterly Operation Report
Grantee Name: |  |  |  |  | ChargePoint, Inc.
Dates Report Covers: |  |  |  |  | Q1'19 (January to March)
Report Submitted By: |  |  |  |  | John Schott
Email Address: |  |  |  |  | john.schott@chargepoint.com
Report Date: |  |  |  |  | 2019-04-17
Please provide a brief narrative on the project progress, including any challenges, that occurred during the reporting period:
ChargePoint is pleased to provide data related to the operation of MEA funded DC Fast Charging stations (DCFC) during Q1'19 - January to March. This is the second quarterly report submitted for the 10 DCFC stations funded through the Alternative Fuel Infrastructure Program. In total, the DC Fast Charging Stations installed by ChargePoint dispensed 2,243 kWh across 174 charging sessions or an average of 13 kWh per session. This level of utilization resulted in the displacement of 282 gallons of gasoline using the industry assumption of .1255 gallons saved per kWh. The average utilization time of the 50kW DCFC was 32 minutes per session, which can provide up to 200 miles of range per hour of charging (RPH) on the ChargePoint Express 200 stations. Uptime for DC Hagerstown station #3 remains at 95% due to the issue reported and addressed last quarter. Uptime for all other stations is 97% because on March 28, 2019, ChargePoint was notified of a potential issue with a component in the CPE200 fast charger that could result in a safety concern. ChargePoint and the station manufacturer, Tritium, worked quickly to investigate the matter and a solution. Beginning March 28, 2019, ChargePoint remotely powered down affected CPE200 stations until a resolution can be identified. The affected stations include all all Box Hill and Cabin John DC fast chargers, and DC Hagerstown Station #4. ChargePoint has initiated a retrofit program to get affected stations back in working order, and will keep the Maryland Energy Administration updated on the timeline for station retrofits.
Station Location |  |  |  |  | Quarterly Data |  |  |  |  | Cumulative Data
Station Name | Station Address | City | Zip | County | % of Time Operational | kWhs consumed | Average Charging Event Duration (mins) | # Of Gasoline Gallons Displaced | # Of Vehicles Using EVSE | kWhs consumed | # Of Gasoline Gallons Displaced
DC CORRIDOR / BOX HILL DC 1 | 3491 Merchant Boulevard | Abingdon | 21009 | Harford County | 97% | 0 | 0 | 0 | 0 | 50 | 6
DC CORRIDOR / BOX HILL DC 2 | 3491 Merchant Boulevard | Abingdon | 21009 | Harford County | 97% | 342.24 | 40 | 42.95 | 40 | 649.24 | 81.95
DC CORRIDOR / BOX HILL DC 3 | 3491 Merchant Boulevard | Abingdon | 21009 | Harford County | 97% | 9 | 14 | 1 | 2 | 139 | 17
DC CORRIDOR / BOX HILL DC 4 | 3491 Merchant Boulevard | Abingdon | 21009 | Harford County | 97% | 182 | 50 | 23 | 11 | 311 | 39
DC CORRIDOR / CABIN JOHN DC1 | 11355 Seven Locks Rd | Potomac | 20854 | Montgomery County | 97% | 255 | 31 | 32 | 24 | 295 | 37
DC CORRIDOR / CABIN JOHN DC2 | 11355 Seven Locks Rd | Potomac | 20854 | Montgomery County | 97% | 128 | 27 | 16 | 16 | 128 | 16
DC CORRIDOR / CABIN JOHN DC3 | 11355 Seven Locks Rd | Potomac | 20854 | Montgomery County | 97% | 39 | 20 | 5 | 5 | 88 | 11
DC CORRIDOR / CABIN JOHN DC4 | 11355 Seven Locks Rd | Potomac | 20854 | Montgomery County | 97% | 493 | 48 | 62 | 31 | 493 | 62
DC CORRIDOR / DC HAGERSTOWN 3 | 17523 Valley Mall Rd | Hagerstown | 21740 | Washington County | 94.8% | 256 | 28 | 32 | 20 | 933 | 117
DC CORRIDOR / DC HAGERSTOWN 4 | 17523 Valley Mall Rd | Hagerstown | 21740 | Washington County | 97% | 539 | 66 | 68 | 25 | 747 | 94
|  |  |  | Total |  | 2243.24 |  | 281.95 | 174 | 3833.24 | 480.95
|  |  |  | Cumulative Avg. | 96.63% | 224.324 | 32.4 | 28.195 | 17.4