## Grantee Quarterly Report
Appendix A
Electric Vehicle Infrastructure Grant Program
Grantee Quarterly Operation Report
Grantee Name: |  |  |  |  | ChargePoint, Inc.
Dates Report Covers: |  |  |  |  | Q1'19 (January to March)
Report Submitted By: |  |  |  |  | John Schott
Email Address: |  |  |  |  | john.schott@chargepoint.com
Report Date: |  |  |  |  | 2019-04-17
Please provide a brief narrative on the project progress, including any challenges, that occurred during the reporting period:
ChargePoint is pleased to provide data related to the operation of MEA funded DC Fast Charging stations (DCFC) during Q1'19 - January to March. In total, the DC Fast Charging Stations installed by ChargePoint dispensed 127 kWh across 13 charging sessions or an average of 10 kWh per session. This level of utilization resulted in the displacement of 16 gallons of gasoline using the industry assumption of .1255 gallons saved per kWh. The average utilization time of the 50kW DCFC was 8 minutes per session, which can provide up to 200 miles of range per hour of charging (RPH) on the ChargePoint Express 200 stations. Hagerstown station #1 was operational for 70% of the time due to the station requiring a new fuse and diode. Clinton Electric was dipactched to repair the station which was fixed and was operational again on 1/17/2019. Hagerstown station #2 was operational for 94% of the time due to a CCS Combo cable swap that was required. The cable swap was completed on 2/15/2019. Both Royal Farms stations were powered down due to a complete rebuild of the entire store, including the parking lot. The DC fast chargers were encapsulated in place for protection and will be turned back on when construction is complete and the store reopens. The anticipated date for reopening the store is currently June 4, 2019. We will keep MEA updated on our progress towards bringing the stations back online over the quarter. ChargePoint anticipates that these station's utilization will continue to increase as knowledge of their existence proliferates and EV adoption increases in the state of Maryland.
Station Location |  |  |  |  | Quarterly Data |  |  |  |  | Cumulative Data
Station Name | Station Address | City | Zip | County | % of Time Operational | kWhs consumed | Average Charging Event Duration (mins) | # Of Gasoline Gallons Displaced | # Of Vehicles Using EVSE | kWhs consumed | # Of Gasoline Gallons Displaced
DCEC / HAGERSTOWN #1 | 17513-17521 Valley Mall Rd | Hagerstown | 21740 | Washington County | 69.5% | 42 | 21 | 5 | 5 | 4068 | 510
DCEC / HAGERSTOWN #2 | 17513-17521 Valley Mall Rd | Hagerstown | 21740 | Washington County | 93.7% | 85 | 40 | 11 | 8 | 4021 | 505
ROYAL FARMS / RFS 102 DC #1 | 10740 Pulaski Hwy | White Marsh | 21162 | Baltimore County | 0% | 0 | 0 | 0 | 0 | 4047 | 508
ROYAL FARMS / RFS 102 DC #2 | 10740 Pulaski Hwy | White Marsh | 21162 | Baltimore County | 0% | 0 | 0 | 0 | 0 | 3682 | 462
|  |  |  | Total |  | 127 |  | 16 | 13 | 15818 | 1985
|  |  |  | Cumulative Avg. | 40.8% | 31.75 | 15.25 | 4 | 3.25