## Grantee Quarterly Report
Alternative Fuel Infrastructure Grant Program
Grantee Quarterly Operation Report
Grantee Name: |  |  |  | Electric Vehicle Institute
Dates Report Covers: |  |  |  | 1Q19 ¦ 1 JANUARY 2019 - 31 MARCH 2019
Submitted By: |  |  |  | Matthew Wade
Email Address |  |  |  | wadem@ev-institute.com
Report Date: |  |  |  | 2019-04-15
Please provide a brief narrative on the project progress, including any challenges, that occurred during the reporting period:
The AFIP FY17 project has been successful from both an operation and deployment perspective. EVI has installed the twenty-two 50kW charging stations at the eight locations. EVI continues to perform its preventive maintenance and operation plan of all operating stations. In regards to unscheduled maintenance/repair, EVI performed the following service(s): 1. Repaired the CCS Combo connector cable assembly at Staion No. 1 and No. 6; and 2. Addressed system operating and communication issues at Station No. 11 and 12.
Station Location
Station ID | Location Name | Station Address | City | Zip | County | Effective Status Date | Fuel Type | % of Time Operational | kWh Consumed | # Of Gasoline Equivalent Gallons Displaced | Average Charging Event Duration (minutes) | # Of Charging Sessions | Average Alternative Fuel Price ($/kWh)
1 | Takoma Park Community Center | 7500 Maple Avenue | Takoma Park | 20912 | Montgomery | 2017-05-03 | 50kW - DC Fast Charger | 100% | 1540 | 45.6973 | 35 | 104 | 0.82
2 | (CLARION INN) | - | Frederick | 21703 | Frederick | - | 50kW - DC Fast Charger | 0% | 0 | 0 | 0 | 0 | -
3 | (CLARION INN) | - | Frederick | 21703 | Frederick | - | 50kW - DC Fast Charger | 0% | 0 | 0 | 0 | 0 | -
4 | (CLARION INN) | - | Frederick | 21703 | Frederick | - | 50kW - DC Fast Charger | 0% | 0 | 0 | 0 | 0 | -
5 | (CLARION INN) | - | Frederick | 21703 | Frederick | - | 50kW - DC Fast Charger | 0% | 0 | 0 | 0 | 0 | -
6 | Greenbelt Roosevelt Center | 25 Crescent Road | Greenbelt | 20770 | Prince Georges | 2017-08-09 | 50kW - DC Fast Charger | 100% | 2129 | 63.1751 | 26 | 171 | 0.82
7 | Maryland House Travel Plaza | I-95, Mile Marker 82 | Aberdeen | 21001 | Hardford | 2017-10-11 | 50kW - DC Fast Charger | 100% | 429.66 | 12.7496 | 14 | 80 | Free
8 | Maryland House Travel Plaza | I-95, Mile Marker 82 | Aberdeen | 21001 | Hardford | 2017-10-11 | 50kW - DC Fast Charger | 100% | 1507.98 | 44.7472 | 40 | 80 | Free
9 | Maryland House Travel Plaza | I-95, Mile Marker 82 | Aberdeen | 21001 | Hardford | 2017-10-11 | 50kW - DC Fast Charger | 100% | 266.07 | 7.8953 | 22 | 28 | Free
10 | Maryland House Travel Plaza | I-95, Mile Marker 82 | Aberdeen | 21001 | Hardford | 2017-10-11 | 50kW - DC Fast Charger | 100% | 968.01 | 28.7243 | 33.6667 | 58 | Free
11 | Chesapeake House Travel Plaza | I-95, Mile Marker 97 | North East | 21901 | Cecil | 2017-11-01 | 50kW - DC Fast Charger | 100% | 1125.22 | 33.3893 | 23 | 94 | Free
12 | Chesapeake House Travel Plaza | I-95, Mile Marker 97 | North East | 21901 | Cecil | 2017-11-01 | 50kW - DC Fast Charger | 100% | 1891.68 | 56.1329 | 25.3333 | 152 | Free
13 | Chesapeake House Travel Plaza | I-95, Mile Marker 97 | North East | 21901 | Cecil | 2017-11-01 | 50kW - DC Fast Charger | 100% | 239.32 | 7.1015 | 22.6667 | 22 | Free
14 | Chesapeake House Travel Plaza | I-95, Mile Marker 97 | North East | 21901 | Cecil | 2017-11-01 | 50kW - DC Fast Charger | 100% | 1561.61 | 46.3386 | 25.6667 | 116 | Free
15 | Maryland House Travel Plaza | I-95, Mile Marker 82 | Aberdeen | 21001 | Hardford | 2018-10-12 | 50kW - DC Fast Charger | 100% | 1244.87 | 36.9398 | 36 | 54 | Free
16 | Maryland House Travel Plaza | I-95, Mile Marker 82 | Aberdeen | 21001 | Hardford | 2018-10-12 | 50kW - DC Fast Charger | 100% | 1029.98 | 30.5632 | 32 | 45 | Free
17 | Hagerstown Central Parking Lot | 14 N Potomac Street | Hagerstown | 21740 | Washington | 2018-12-13 | 50kW - DC Fast Charger | 100% | 126 | 3.7389 | 31 | 11 | Free
18 | Hagerstown Central Parking Lot | 14 N Potomac Street | Hagerstown | 21740 | Washington | 2018-12-13 | 50kW - DC Fast Charger | 100% | 116 | 3.4421 | 36 | 8 | Free
19 | Hagerstown Central Parking Lot | 14 N Potomac Street | Hagerstown | 21740 | Washington | 2018-12-13 | 50kW - DC Fast Charger | 100% | 208 | 6.1721 | 38 | 14 | Free
20 | Hagerstown Central Parking Lot | 14 N Potomac Street | Hagerstown | 21740 | Washington | 2018-12-13 | 50kW - DC Fast Charger | 100% | 225 | 6.6766 | 29 | 21 | Free
21 | Chesapeake House Travel Plaza | I-95, Mile Marker 97 | North East | 21901 | Cecil | 2019-02-26 | 50kW - DC Fast Charger | 100% | 766.35 | 22.7404 | 33 | 46 | Free
22 | Chesapeake House Travel Plaza | I-95, Mile Marker 97 | North East | 21901 | Cecil | 2019-02-26 | 50kW - DC Fast Charger | 100% | 604.68 | 17.943 | 34 | 41 | Free