## Grantee Quarterly Report
Appendix A
Alternative Fuel Infrastructure Grant Program
Grantee Quarterly Operation Report
Grantee Name: |  |  |  |  | ChargePoint, Inc.
Dates Report Covers: |  |  |  |  | Q2'19 (April to June)
Report Submitted By: |  |  |  |  | John Schott
Email Address: |  |  |  |  | john.schott@chargepoint.com
Report Date: |  |  |  |  | 2019-07-24
Please provide a brief narrative on the project progress, including any challenges, that occurred during the reporting period:
ChargePoint is pleased to provide data related to the operation of MEA funded DC Fast Charging stations (DCFC) during Q2'19 - April to June. In total, the DCFC installed by ChargePoint dispensed 1,637 kWh across 100 charging sessions or an average of 16.4 kWh per session. This level of utilization resulted in the displacement of 205 gallons of gasoline using the industry assumption of .1255 gallons saved per kWh. The average utilization time of the 50kW DCFC was 30 minutes per session, which can provide up to 200 miles of range per hour of charging (RPH) on the ChargePoint Express 200 stations. Uptime for all 10 DCFC was significantly impacted due to ChargePoint being notified of a potential issue with a component in the CPE200 fast charger that could result in a safety concern. ChargePoint and the station manufacturer, Tritium, worked quickly to investigate the matter. Beginning March 28, 2019, ChargePoint remotely powered down affected CPE200 stations until a resolution could be identified. The affected stations included all DCFC at Box Hill and Cabin John and DC Hagerstown Station #4. On May 23, 2019 ChargePoint also remotely powered down DC Hagerstown Station #3 after learning from Tritium that this station also potentially had the same safety concern as the other chargers. ChargePoint initiated a retrofit program to get affected stations back in working order, and all stations except for Hagerstown #3 have been repaired and are operational. ChargePoint will keep the Maryland Energy Administration updated on the timeline for retrofitting this station. The date ranges for which station were non-operational are listed below: Box Hill DC 1, 2, 3 & 4: March 28, 2019 - May 8, 2019 Cabin John DC 1, 2, 3 & 4: March 28, 2019 - May 4, 2019 Hagerstown 3: May 23, 2019 - June 30, 2019 Hagerstown 4: March 28, 2019 - May 11, 2019
Station Location |  |  |  |  | Quarterly Data |  |  |  |  | Cumulative Data
Station Name | Station Address | City | Zip | County | % of Time Operational | kWhs consumed | Average Charging Event Duration (mins) | # Of Gasoline Gallons Displaced | # Of Vehicles Using EVSE | kWhs consumed | # Of Gasoline Gallons Displaced
DC CORRIDOR / BOX HILL DC 1 | 3491 Merchant Boulevard | Abingdon | 21009 | Harford County | 76.8% | 23.288 | 21.8056 | 2.922 | 3 | 73.288 | 8.922
DC CORRIDOR / BOX HILL DC 2 | 3491 Merchant Boulevard | Abingdon | 21009 | Harford County | 76.8% | 50.144 | 23.9375 | 6.294 | 4 | 699.144 | 88.294
DC CORRIDOR / BOX HILL DC 3 | 3491 Merchant Boulevard | Abingdon | 21009 | Harford County | 76.8% | 144.446 | 44.1167 | 18.128 | 10 | 283.446 | 35.128
DC CORRIDOR / BOX HILL DC 4 | 3491 Merchant Boulevard | Abingdon | 21009 | Harford County | 76.8% | 15.422 | 11.5833 | 1.935 | 2 | 326.422 | 40.935
DC CORRIDOR / CABIN JOHN DC1 | 11355 Seven Locks Rd | Potomac | 20854 | Montgomery County | 79.01% | 65.301 | 51.9375 | 8.195 | 4 | 360.301 | 45.195
DC CORRIDOR / CABIN JOHN DC2 | 11355 Seven Locks Rd | Potomac | 20854 | Montgomery County | 79.01% | 0 | 0 | 0 | 0 | 128 | 16
DC CORRIDOR / CABIN JOHN DC3 | 11355 Seven Locks Rd | Potomac | 20854 | Montgomery County | 79.01% | 115.719 | 28.7083 | 14.522 | 8 | 203.719 | 25.522
DC CORRIDOR / CABIN JOHN DC4 | 11355 Seven Locks Rd | Potomac | 20854 | Montgomery County | 79.01% | 391.513 | 31.8819 | 49.135 | 23 | 884.513 | 111.135
DC CORRIDOR / DC HAGERSTOWN 3 | 17523 Valley Mall Rd | Hagerstown | 21740 | Washington County | 75.97% | 417.974 | 44.0894 | 52.456 | 22 | 1350.974 | 169.456
DC CORRIDOR / DC HAGERSTOWN 4 | 17523 Valley Mall Rd | Hagerstown | 21740 | Washington County | 75.14% | 413.35 | 37.4153 | 51.875 | 24 | 1160.35 | 145.875
|  |  |  | Total |  | 1637.157 |  | 205.462 | 100 | 5470.157 | 686.462
|  |  |  | Cumulative Avg. | 77.85% | 163.7157 | 29.5475 | 20.5462 | 10