## Grantee Quarterly Report
Alternative Fuel Infrastructure Grant Program
Grantee Quarterly Operation Report
Grantee Name: |  |  |  | Electric Vehicle Institute
Dates Report Covers: |  |  |  | 3Q19 ¦ 1 JULY 2019 - 30 SEPTEMBER 2019
Submitted By: |  |  |  | Matthew Wade
Email Address |  |  |  | wadem@ev-institute.com
Report Date: |  |  |  | 2019-10-15
Please provide a brief narrative on the project progress, including any challenges, that occurred during the reporting period:
The AFIP FY17 project has been successful from both an operation and deployment perspective. EVI has installed the twenty-two 50kW charging stations at the eight locations. EVI continues to perform its preventive maintenance and operation plan of all operating stations. In regards to unscheduled maintenance/repair, EVI performed the following service(s): repaired the human interface and payment system; processed the critcal power systems; and repaired system operating and communication issues.
Station Location
Station ID | Location Name | Station Address | City | Zip | County | Effective Status Date | Fuel Type | % of Time Operational | kWh Consumed | # Of Gasoline Equivalent Gallons Displaced | Average Charging Event Duration (minutes) | # Of Charging Sessions | Average Alternative Fuel Price ($/kWh)
1 | Takoma Park Community Center | 7500 Maple Avenue | Takoma Park | 20912 | Montgomery | 2017-05-03 | 50kW - DC Fast Charger | 100% | 1934.37 | 57.3997 | 28 | 132 | 0.82
2 | (CLARION INN) | - | Frederick | 21703 | Frederick | - | 50kW - DC Fast Charger | 0% | 0 | 0 | 0 | 0 | -
3 | (CLARION INN) | - | Frederick | 21703 | Frederick | - | 50kW - DC Fast Charger | 0% | 0 | 0 | 0 | 0 | -
4 | (CLARION INN) | - | Frederick | 21703 | Frederick | - | 50kW - DC Fast Charger | 0% | 0 | 0 | 0 | 0 | -
5 | (CLARION INN) | - | Frederick | 21703 | Frederick | - | 50kW - DC Fast Charger | 0% | 0 | 0 | 0 | 0 | -
6 | Greenbelt Roosevelt Center | 25 Crescent Road | Greenbelt | 20770 | Prince Georges | 2017-08-09 | 50kW - DC Fast Charger | 100% | 985.3 | 29.2374 | 25 | 73 | 0.82
7 | Maryland House Travel Plaza | I-95, Mile Marker 82 | Aberdeen | 21001 | Hardford | 2017-10-11 | 50kW - DC Fast Charger | 100% | 487 | 14.451 | 37 | 28 | Free
8 | Maryland House Travel Plaza | I-95, Mile Marker 82 | Aberdeen | 21001 | Hardford | 2017-10-11 | 50kW - DC Fast Charger | 100% | 881.52 | 26.1579 | 17.3333 | 117 | Free
9 | Maryland House Travel Plaza | I-95, Mile Marker 82 | Aberdeen | 21001 | Hardford | 2017-10-11 | 50kW - DC Fast Charger | 100% | 2153.51 | 63.9024 | 30 | 131 | Free
10 | Maryland House Travel Plaza | I-95, Mile Marker 82 | Aberdeen | 21001 | Hardford | 2017-10-11 | 50kW - DC Fast Charger | 100% | 1246.35 | 36.9837 | 33 | 74 | Free
11 | Chesapeake House Travel Plaza | I-95, Mile Marker 97 | North East | 21901 | Cecil | 2017-11-01 | 50kW - DC Fast Charger | 100% | 1164.13 | 34.5439 | 24.3333 | 99 | Free
12 | Chesapeake House Travel Plaza | I-95, Mile Marker 97 | North East | 21901 | Cecil | 2017-11-01 | 50kW - DC Fast Charger | 100% | 1871.08 | 55.5217 | 24 | 153 | Free
13 | Chesapeake House Travel Plaza | I-95, Mile Marker 97 | North East | 21901 | Cecil | 2017-11-01 | 50kW - DC Fast Charger | 100% | 1455.35 | 43.1855 | 22 | 125 | Free
14 | Chesapeake House Travel Plaza | I-95, Mile Marker 97 | North East | 21901 | Cecil | 2017-11-01 | 50kW - DC Fast Charger | 100% | 1950.01 | 57.8638 | 23 | 162 | Free
15 | Maryland House Travel Plaza | I-95, Mile Marker 82 | Aberdeen | 21001 | Hardford | 2018-10-12 | 50kW - DC Fast Charger | 100% | 1254.23 | 37.2175 | 31.6667 | 72 | Free
16 | Maryland House Travel Plaza | I-95, Mile Marker 82 | Aberdeen | 21001 | Hardford | 2018-10-12 | 50kW - DC Fast Charger | 100% | 728.72 | 21.6237 | 39.6667 | 44 | Free
17 | Hagerstown Central Parking Lot | 14 N Potomac Street | Hagerstown | 21740 | Washington | 2018-12-13 | 50kW - DC Fast Charger | 100% | 919.39 | 27.2816 | 35 | 55 | Free
18 | Hagerstown Central Parking Lot | 14 N Potomac Street | Hagerstown | 21740 | Washington | 2018-12-13 | 50kW - DC Fast Charger | 100% | 517.21 | 15.3475 | 40.3333 | 29 | Free
19 | Hagerstown Central Parking Lot | 14 N Potomac Street | Hagerstown | 21740 | Washington | 2018-12-13 | 50kW - DC Fast Charger | 100% | 549.97 | 16.3196 | 32 | 39 | Free
20 | Hagerstown Central Parking Lot | 14 N Potomac Street | Hagerstown | 21740 | Washington | 2018-12-13 | 50kW - DC Fast Charger | 100% | 529.48 | 15.7116 | 33.3333 | 30 | Free
21 | Chesapeake House Travel Plaza | I-95, Mile Marker 97 | North East | 21901 | Cecil | 2019-02-26 | 50kW - DC Fast Charger | 100% | 746.63 | 22.1552 | 33 | 49 | Free
22 | Chesapeake House Travel Plaza | I-95, Mile Marker 97 | North East | 21901 | Cecil | 2019-02-26 | 50kW - DC Fast Charger | 100% | 483.3 | 14.3412 | 29 | 41 | Free