## Grantee Quarterly Report
Alternative Fuel Infrastructure Grant Program
Grantee Quarterly Operation Report
Grantee Name: |  |  |  | Electric Vehicle Institute
Dates Report Covers: |  |  |  | 4Q19 ¦ 1 OCTOBER 2019 - 31 DECEMBER 2019
Submitted By: |  |  |  | Matthew Wade
Email Address |  |  |  | wadem@ev-institute.com
Report Date: |  |  |  | 2020-01-15
Please provide a brief narrative on the project progress, including any challenges, that occurred during the reporting period:
The AFIP FY17 project has been successful from both an operation and deployment perspective. EVI has installed the twenty-two 50kW charging stations at the eight locations. EVI continues to perform its preventive maintenance and operation plan of all operating stations. In regards to unscheduled maintenance/repair, EVI performed the following service(s): Hagerstown DCFCs received new communications systems during the reporting period; repaired the human interface and payment system; processed the critcal power systems; and repaired system operating and communication issues.
Station Location
Station ID | Location Name | Station Address | City | Zip | County | Effective Status Date | Fuel Type | % of Time Operational | kWh Consumed | # Of Gasoline Equivalent Gallons Displaced | Average Charging Event Duration (minutes) | # Of Charging Sessions | Average Alternative Fuel Price ($/kWh)
1 | Takoma Park Community Center | 7500 Maple Avenue | Takoma Park | 20912 | Montgomery | 2017-05-03 | 50kW - DC Fast Charger | 100% | 1803.35 | 53.5119 | 36 | 112 | 0.82
2 | (CLARION INN) | - | Frederick | 21703 | Frederick | - | 50kW - DC Fast Charger | 0% | 0 | 0 | 0 | 0 | -
3 | (CLARION INN) | - | Frederick | 21703 | Frederick | - | 50kW - DC Fast Charger | 0% | 0 | 0 | 0 | 0 | -
4 | (CLARION INN) | - | Frederick | 21703 | Frederick | - | 50kW - DC Fast Charger | 0% | 0 | 0 | 0 | 0 | -
5 | (CLARION INN) | - | Frederick | 21703 | Frederick | - | 50kW - DC Fast Charger | 0% | 0 | 0 | 0 | 0 | -
6 | Greenbelt Roosevelt Center | 25 Crescent Road | Greenbelt | 20770 | Prince Georges | 2017-08-09 | 50kW - DC Fast Charger | 100% | 1582.8 | 46.9674 | 25 | 122 | 0.82
7 | Maryland House Travel Plaza | I-95, Mile Marker 82 | Aberdeen | 21001 | Hardford | 2017-10-11 | 50kW - DC Fast Charger | 100% | 151.39 | 4.4923 | 28.5 | 15 | Free
8 | Maryland House Travel Plaza | I-95, Mile Marker 82 | Aberdeen | 21001 | Hardford | 2017-10-11 | 50kW - DC Fast Charger | 100% | 1127.03 | 33.443 | 31 | 74 | Free
9 | Maryland House Travel Plaza | I-95, Mile Marker 82 | Aberdeen | 21001 | Hardford | 2017-10-11 | 50kW - DC Fast Charger | 100% | 319.82 | 9.4902 | 32 | 19 | Free
10 | Maryland House Travel Plaza | I-95, Mile Marker 82 | Aberdeen | 21001 | Hardford | 2017-10-11 | 50kW - DC Fast Charger | 100% | 967.65 | 28.7136 | 32.3333 | 55 | Free
11 | Chesapeake House Travel Plaza | I-95, Mile Marker 97 | North East | 21901 | Cecil | 2017-11-01 | 50kW - DC Fast Charger | 100% | 1239.19 | 36.7712 | 22.5 | 106 | Free
12 | Chesapeake House Travel Plaza | I-95, Mile Marker 97 | North East | 21901 | Cecil | 2017-11-01 | 50kW - DC Fast Charger | 100% | 1463.58 | 43.4297 | 24 | 111 | Free
13 | Chesapeake House Travel Plaza | I-95, Mile Marker 97 | North East | 21901 | Cecil | 2017-11-01 | 50kW - DC Fast Charger | 100% | 465.27 | 13.8062 | 23.3333 | 36 | Free
14 | Chesapeake House Travel Plaza | I-95, Mile Marker 97 | North East | 21901 | Cecil | 2017-11-01 | 50kW - DC Fast Charger | 100% | 1327.85 | 39.4021 | 24.6667 | 98 | Free
15 | Maryland House Travel Plaza | I-95, Mile Marker 82 | Aberdeen | 21001 | Hardford | 2018-10-12 | 50kW - DC Fast Charger | 100% | 1766.29 | 52.4122 | 32.3333 | 98 | Free
16 | Maryland House Travel Plaza | I-95, Mile Marker 82 | Aberdeen | 21001 | Hardford | 2018-10-12 | 50kW - DC Fast Charger | 100% | 692.94 | 20.562 | 33 | 36 | Free
17 | Hagerstown Central Parking Lot | 14 N Potomac Street | Hagerstown | 21740 | Washington | 2018-12-13 | 50kW - DC Fast Charger | 100% | 444.66 | 13.1947 | 37 | 29 | Free
18 | Hagerstown Central Parking Lot | 14 N Potomac Street | Hagerstown | 21740 | Washington | 2018-12-13 | 50kW - DC Fast Charger | 100% | 1234.51 | 36.6323 | 39.6667 | 66 | Free
19 | Hagerstown Central Parking Lot | 14 N Potomac Street | Hagerstown | 21740 | Washington | 2018-12-13 | 50kW - DC Fast Charger | 100% | 232.32 | 6.8938 | 43.6667 | 19 | Free
20 | Hagerstown Central Parking Lot | 14 N Potomac Street | Hagerstown | 21740 | Washington | 2018-12-13 | 50kW - DC Fast Charger | 100% | 204.55 | 6.0697 | 41 | 9 | Free
21 | Chesapeake House Travel Plaza | I-95, Mile Marker 97 | North East | 21901 | Cecil | 2019-02-26 | 50kW - DC Fast Charger | 100% | 350.8 | 10.4095 | 33 | 18 | Free
22 | Chesapeake House Travel Plaza | I-95, Mile Marker 97 | North East | 21901 | Cecil | 2019-02-26 | 50kW - DC Fast Charger | 100% | 805.31 | 23.8964 | 29.6667 | 41 | Free