## Grantee Quarterly Report
Alternative Fuel Infrastructure Grant Program
Grantee Quarterly Operation Report
|  | Grantee Name: |  |  |  | Electric Vehicle Institute
|  | Dates Report Covers: |  |  |  | 1Q20 ¦ 1 JANUARY 2020 - 31 MARCH 2020
|  | Submitted By: |  |  |  | Matthew Wade
|  | Email Address |  |  |  | wadem@ev-institute.com
|  | Report Date: |  |  |  | 2020-04-15
Please provide a brief narrative on the project progress, including any challenges, that occurred during the reporting period:
The AFIP project has been successful from both an operation and deployment perspective. EVI has successfully completed the construction phase of AFIP FY2016 and deployed all fourteen stations as listed in this report. Moreover, EVI continues to perform its preventive maintenance and operation plan of all fourteen stations. In regards to unscheduled maintenance/repair, EVI performed onsite services, which include replacement of MCU and SECC circuit board;updated operating system; replacement of celluar modem; replacement of CCS and CHADEMO charging cables; repaired cord managment system; and, repair/replacement of monitoring system. Further, EVI is continuing its work with BGE and Facility Engineers to complete BGE's electrical service repair work at the Forest Park Library Branch. However, the service associated to this repair work has been further delayed due to COVID-19 impacts on safety issues and limited resources.
Station Location
| No. | Station Address | City | Zip | County | Effective Status Date | Fuel Type | % of Time Operational | kWh Consumed | # Of Gasoline Equivalent Gallons Displaced | Average Charging Event Duration (minutes) | # Of Charging Sessions | Average Alternative Fuel Price ($/kWh)
2 | 1 | 1303 Orleans Street | Baltimore | 21231 | Baltimore City | 2016-08-16 | 50kW - DC Fast Charger | 100% | 1364.88 | 40.5009 | 42 | 71 | Free
1 | 2 | 6310 Reisterstown Road | Baltimore | 21215 | Baltimore City | 2016-09-07 | 50kW - DC Fast Charger | 100% | 2079.72 | 61.7128 | 37 | 197 | Free
3 | 3 | 1101 Russell Street | Baltimore | 21230 | Baltimore City | 2016-09-29 | 50kW - DC Fast Charger | 100% | 32.63 | 0.96825 | 25 | 2 | Free
4 | 4 | 1251 Light Street | Baltimore | 21230 | Baltimore City | 2016-10-07 | 50kW - DC Fast Charger | 100% | 2186.02 | 64.8671 | 18 | 243 | Free
5 | 5 | 5910 Harford Road | Baltimore | 21214 | Baltimore City | 2016-11-10 | 50kW - DC Fast Charger | 100% | 309.45 | 9.1825 | 20 | 29 | Free
6 | 6 | 5108 Roland Avenue | Baltimore | 21210 | Baltimore City | 2016-11-18 | 50kW - DC Fast Charger | 100% | 7619.05 | 226.0846 | 24.5 | 665 | Free
8 | 7 | 3023 Garrison Boulevard | Baltimore | 21216 | Baltimore City | 2016-12-13 | 50kW - DC Fast Charger | 0% | 0 | 0 | 0 | 0 | Free
7 | 8 | 3100 Swann Drive | Baltimore | 21217 | Baltimore City | 2017-01-06 | 50kW - DC Fast Charger | 100% | 3530.23 | 104.7546 | 24 | 310 | Free
9 | 9 | 3801 Erdman Avenue | Baltimore | 21213 | Baltimore City | 2017-02-06 | 50kW - DC Fast Charger | 100% | 1136.43 | 33.722 | 25.5 | 111 | Free
10 | 10 | 3001 Boston Street | Baltimore | 21224 | Baltimore City | 2017-03-08 | 50kW - DC Fast Charger | 100% | 2138.72 | 63.4635 | 41 | 198 | Free
13 | 11 | 4999 Windsor Mill Road | Baltimore | 21207 | Baltimore City | 2017-03-09 | 50kW - DC Fast Charger | 100% | 2466.5 | 73.1899 | 25.25 | 209 | Free
11 | 12 | 27 S Patterson Park Ave | Baltimore | 21231 | Baltimore City | 2017-03-17 | 50kW - DC Fast Charger | 100% | 3141.01 | 93.205 | 56 | 284 | Free
12 | 13 | 101 West Dickman Street | Baltimore | 21230 | Baltimore City | 2017-03-28 | 50kW - DC Fast Charger | 100% | 2513.72 | 74.5911 | 43.25 | 158 | Free
14 | 14 | 7000 Carroll Avenue | Takoma Park | 20912 | Montgomery | 2017-11-28 | 50kW - DC Fast Charger | 100% | 30.71 | 0.91128 | 18 | 3 | 0.64