## Grantee Quarterly Report
Alternative Fuel Infrastructure Grant Program
Grantee Quarterly Operation Report
Grantee Name: |  |  |  | Electric Vehicle Institute
Dates Report Covers: |  |  |  | 1Q20 ¦ 1 JANUARY 2020 - 31 MARCH 2020
Submitted By: |  |  |  | Matthew Wade
Email Address |  |  |  | wadem@ev-institute.com
Report Date: |  |  |  | 2020-04-15
Please provide a brief narrative on the project progress, including any challenges, that occurred during the reporting period:
The AFIP FY18 project has been successful from both an operation and deployment perspective. EVI has installed twelve of sixteen 50kW charging stations at four of the seven locations. EVI repaired the human interface and payment system; processed the critcal power systems; and repaired system operating and communication issues.
Station Location
Station ID | Location Name | Station Address | City | Zip | County | Effective Status Date | Fuel Type | % of Time Operational | kWh Consumed | # Of Gasoline Equivalent Gallons Displaced | Average Charging Event Duration (minutes) | # Of Charging Sessions | Average Alternative Fuel Price ($/kWh)
1 | Hyattsville Municipal Building | 4310 Gallatin St | Hyattsville | 20781 | Prince Georges | 2018-08-15 | 50kW - DC Fast Charger | 100% | 407.8 | 12.1009 | 29 | 28 | Free
2 | Hyattsville Municipal Building | 4310 Gallatin St | Hyattsville | 20781 | Prince Georges | 2018-08-15 | 50kW - DC Fast Charger | 100% | 8454.28 | 250.8688 | 27 | 716 | Free
3 | OC Convention Center | 4001 Coastal Hwy | Ocean City | 21842 | Worcester | 2018-08-21 | 50kW - DC Fast Charger | 100% | 34.75 | 1.0312 | 42 | 1.5 | Free
4 | OC Convention Center | 4001 Coastal Hwy | Ocean City | 21842 | Worcester | 2018-08-21 | 50kW - DC Fast Charger | 100% | 47.87 | 1.4205 | 42 | 2 | Free
5 | Vienna Old Ocean Gateway | 307 Old Ocean Gateway | Vienna | 21869 | Dorchester | 2018-11-30 | 50kW - DC Fast Charger | 100% | 32.15 | 0.95401 | 5 | 25 | Free
6 | Vienna Old Ocean Gateway | 307 Old Ocean Gateway | Vienna | 21869 | Dorchester | 2018-11-30 | 50kW - DC Fast Charger | 100% | 227.9 | 6.7626 | 17 | 24 | Free
7 | RS Automotive | 7224 Carroll Avenue | Takoma Park | 20912 | Prince Georges | 2019-10-11 | 50kW - DC Fast Charger | 100% | 1238.41 | 36.7481 | 39 | 74 | Free
8 | RS Automotive | 7224 Carroll Avenue | Takoma Park | 20912 | Prince Georges | 2019-10-11 | 50kW - DC Fast Charger | 100% | 206.42 | 6.1252 | 32 | 22 | Free
9 | RS Automotive | 7224 Carroll Avenue | Takoma Park | 20912 | Prince Georges | 2019-10-11 | 50kW - DC Fast Charger | 100% | 1240.74 | 36.8172 | 40 | 61 | Free
10 | RS Automotive | 7224 Carroll Avenue | Takoma Park | 20912 | Prince Georges | 2019-10-11 | 50kW - DC Fast Charger | 100% | 790.64 | 23.4611 | 48 | 45 | Free
11 | Western Maryland Rail Trail Parking Lot | N Church St & Canal St | Hancock | 21750 | Frederick | 2019-12-05 | 50kW - DC Fast Charger | 100% | 119.42 | 3.5436 | 8 | 28 | Free
12 | Western Maryland Rail Trail Parking Lot | N Church St & Canal St | Hancock | 21750 | Frederick | 2019-12-05 | 50kW - DC Fast Charger | 100% | 25.58 | 0.75905 | 8 | 8 | Free