## Grantee Quarterly Report
Alternative Fuel Infrastructure Grant Program
Grantee Quarterly Operation Report
Grantee Name: |  |  |  | Electric Vehicle Institute
Dates Report Covers: |  |  |  | 3Q20 ¦ 1 APRIL 2020 - 30 JUNE 2020
Submitted By: |  |  |  | Matthew Wade
Email Address |  |  |  | wadem@ev-institute.com
Report Date: |  |  |  | 2020-07-15
Please provide a brief narrative on the project progress, including any challenges, that occurred during the reporting period:
The AFIP FY17 project has been successful from both an operation and deployment perspective. EVI has installed the twenty-two 50kW charging stations at the eight locations. EVI continues to perform its preventive maintenance and operation plan of all operating stations. In regards to unscheduled maintenance/repair, EVI performed services to repair communication systems, the human interface and payment system, the critcal power systems, and the system operating issues.
Station Location
Station ID | Location Name | Station Address | City | Zip | County | Effective Status Date | Fuel Type | % of Time Operational | kWh Consumed | # Of Gasoline Equivalent Gallons Displaced | Average Charging Event Duration (minutes) | # Of Charging Sessions | Average Alternative Fuel Price ($/kWh)
1 | Takoma Park Community Center | 7500 Maple Avenue | Takoma Park | 20912 | Montgomery | 2017-05-03 | 50kW - DC Fast Charger | 100% | 1243.35 | 36.8947 | 27.3333 | 86 | 0.82
2 | (CLARION INN) | - | Frederick | 21703 | Frederick | - | 50kW - DC Fast Charger | 0% | 0 | 0 | 0 | 0 | -
3 | (CLARION INN) | - | Frederick | 21703 | Frederick | - | 50kW - DC Fast Charger | 0% | 0 | 0 | 0 | 0 | -
4 | (CLARION INN) | - | Frederick | 21703 | Frederick | - | 50kW - DC Fast Charger | 0% | 0 | 0 | 0 | 0 | -
5 | (CLARION INN) | - | Frederick | 21703 | Frederick | - | 50kW - DC Fast Charger | 0% | 0 | 0 | 0 | 0 | -
6 | Greenbelt Roosevelt Center | 25 Crescent Road | Greenbelt | 20770 | Prince Georges | 2017-08-09 | 50kW - DC Fast Charger | 100% | 421.96 | 12.5211 | 27 | 29 | 0.82
7 | Maryland House Travel Plaza | I-95, Mile Marker 82 | Aberdeen | 21001 | Hardford | 2017-10-11 | 50kW - DC Fast Charger | 100% | 378.42 | 11.2291 | 32.6667 | 20 | Free
8 | Maryland House Travel Plaza | I-95, Mile Marker 82 | Aberdeen | 21001 | Hardford | 2017-10-11 | 50kW - DC Fast Charger | 100% | 150.51 | 4.4662 | 24.3333 | 12 | Free
9 | Maryland House Travel Plaza | I-95, Mile Marker 82 | Aberdeen | 21001 | Hardford | 2017-10-11 | 50kW - DC Fast Charger | 100% | 45.36 | 1.346 | 34 | 4 | Free
10 | Maryland House Travel Plaza | I-95, Mile Marker 82 | Aberdeen | 21001 | Hardford | 2017-10-11 | 50kW - DC Fast Charger | 100% | 123.18 | 3.6552 | 28 | 7 | Free
11 | Chesapeake House Travel Plaza | I-95, Mile Marker 97 | North East | 21901 | Cecil | 2017-11-01 | 50kW - DC Fast Charger | 100% | 189.68 | 5.6285 | 26 | 13 | Free
12 | Chesapeake House Travel Plaza | I-95, Mile Marker 97 | North East | 21901 | Cecil | 2017-11-01 | 50kW - DC Fast Charger | 100% | 37.76 | 1.1205 | 65 | 1 | Free
13 | Chesapeake House Travel Plaza | I-95, Mile Marker 97 | North East | 21901 | Cecil | 2017-11-01 | 50kW - DC Fast Charger | 100% | 182.17 | 5.4056 | 28 | 12 | Free
14 | Chesapeake House Travel Plaza | I-95, Mile Marker 97 | North East | 21901 | Cecil | 2017-11-01 | 50kW - DC Fast Charger | 100% | 326.27 | 9.6816 | 24 | 23 | Free
15 | Maryland House Travel Plaza | I-95, Mile Marker 82 | Aberdeen | 21001 | Hardford | 2018-10-12 | 50kW - DC Fast Charger | 100% | 386.11 | 11.4573 | 31 | 18 | Free
16 | Maryland House Travel Plaza | I-95, Mile Marker 82 | Aberdeen | 21001 | Hardford | 2018-10-12 | 50kW - DC Fast Charger | 100% | 109.69 | 3.2549 | 26 | 8 | Free
17 | Hagerstown Central Parking Lot | 14 N Potomac Street | Hagerstown | 21740 | Washington | 2018-12-13 | 50kW - DC Fast Charger | 100% | 193.9 | 5.7537 | 30.3333 | 12 | Free
18 | Hagerstown Central Parking Lot | 14 N Potomac Street | Hagerstown | 21740 | Washington | 2018-12-13 | 50kW - DC Fast Charger | 100% | 357.8 | 10.6172 | 45.6667 | 16 | Free
19 | Hagerstown Central Parking Lot | 14 N Potomac Street | Hagerstown | 21740 | Washington | 2018-12-13 | 50kW - DC Fast Charger | 100% | 400.55 | 11.8858 | 41.2 | 22 | Free
20 | Hagerstown Central Parking Lot | 14 N Potomac Street | Hagerstown | 21740 | Washington | 2018-12-13 | 50kW - DC Fast Charger | 100% | 577.27 | 17.1297 | 39 | 26 | Free
21 | Chesapeake House Travel Plaza | I-95, Mile Marker 97 | North East | 21901 | Cecil | 2019-02-26 | 50kW - DC Fast Charger | 100% | 950 | 28.1899 | 37 | 42 | Free
22 | Chesapeake House Travel Plaza | I-95, Mile Marker 97 | North East | 21901 | Cecil | 2019-02-26 | 50kW - DC Fast Charger | 100% | 400.12 | 11.873 | 41.3333 | 19 | Free